## Integration Project Plan
Integration Plan & Project Management Tool
Priority Area | Action Target | Tasks | Primary Owner | Secondary Owner | Deadline | Status | Tools | Success/Challenges
Name the Priority Areas your integration strategy will target, be based on the drivers of segregation in your district that you've identified. | List the Action Targets you set to support your Outcome Targets in each of your Priority Areas. Copy the target into as many rows as needed in order to list all tasks you will need to complete in order to meet this target. | Draft all tasks needed to operationalize and implement the work that needs to be done in order to meet your Action Targets. This is where you should be as detailed as possible. Enter each task in a new row, so that you can record the owner of each task and track the status of each task as you progress through your plan. (In the example below, there are 4 tasks associated with the Action Target in Column C, which is why the same Action Target is copied into 4 rows in Column C). | Name the district role of the person who is the primary owner of this action. | Name the district or partner role of the person who is the secondary owner of this action. | Set a deadline for this task. | Use the status tab to update progress on given task. | Please list the tools needed to complete tasks and measure results. An idea of what may be included to share is as follows: survey results, student achievement data analysis, attendance data analysis, curriculum audits, rubrics for teacher evaluation, student or parent surveys, etc. | Note the success(es) or challenge(s) you faced when you approached this task. This will help you understand what contributed to your wins and losses when you report your performance at the end of this first school year if you keep adequate notes throughout the year!
EXAMPLES ARE PROVIDED IN ROWS 7-11.
Increasing Access to Rigorous Middle School Programs | Hold 3 Town Hall meetings in school year 23-24 to determine family choice programs for middle schools. Collect meeting agenda minutes during each Town Hall and a final vote count for middle school programs and middle school admissions set-aside targets. | Prepare deck in English and Spanish for family engagement town hall meetings. | Director of Secondary | WXY Consulting | 2023-08-31 | Completed | Orientation PowerPoint (English & Spanish version) | We tested different times for each town hall to see which yielded the highest engagement. Meetings directly after school were the most popular. Having materials translated to various languages seemed to increase attendance to town hall meetings
Increasing Access to Rigorous Middle School Programs | Hold 3 Town Hall meetings in school year 23-24 to determine family choice programs for middle schools. Collect meeting agenda minutes during each Town Hall and a final vote count for middle school programs and middle school admissions set-aside targets. | Calendar town hall meetings with all schools, sharing with all 5th grade families. | Secretary of the Director of Secondary | WXY Consulting | 2023-09-30 | On Track | Town Hall Registration Form & Calendar Invites | TBD
Increasing Access to Rigorous Middle School Programs | Hold 3 Town Hall meetings in school year 23-24 to determine family choice programs for middle schools. Collect meeting agenda minutes during each Town Hall and a final vote count for middle school programs and middle school admissions set-aside targets. | Calendar principal update meetings after townhalls | Secretary of the Director of Secondary | WXY Consulting | 2023-09-30 | To Do | Accepted Calendar Invites | TBD
Increasing Access to Rigorous Middle School Programs | Hold 3 Town Hall meetings in school year 23-24 to determine family choice programs for middle schools. Collect meeting agenda minutes during each Town Hall and a final vote count for middle school programs and middle school admissions set-aside targets. | Create program content for 3 town hall meetings | Director of Secondary's Assistant | WXY Consulting | 2023-10-13 | To Do | Orientation PowerPoint, Presenter/Speaker Notes, Handouts/Flyers, Voting Form, & Satisfaction Survey | TBD
Increasing Access to Rigorous Middle School Programs | By May 2025, audit admissions and enrollment at every middle school against admission set-aside goals: 52% FRPL, 12% special education, 13% living in temporary housing. Once analysis is complete, principals in partnership with the Director of Secondary will strategize admissions shifts between schools, as needed, to ensure all isolated and identified student subgroups receive their 1st, 2nd, or 3rd choice. | Audit admissions and enrollment for every middle school against set-aside allocations | Director of Secondary | Data Analyst | 2025-05-30 | To Do | Demographically-disaggregated admission & enrollment data for each middle school; set-aside targets | TBD