## Cost Proposal - Summary
RFP #24-023 GRANTS FINANCIAL MANAGEMENT SYSTEM (GFMS) COST PROPOSAL
CONTRACT TERM: SEPTEMBER 15, 2024 - FEBRUARY 13, 2029
BID SUBMITTED BY: | <insert name of company>
Milestone/Deliverable Based Cost Proposal
Payment Milestone | Milestone Feature | Deliverable | Estimate of Cost (in whole dollars) (to be completed by Bidder) | Milestone Timeline | Tentative Due Date
GFMS-Milestone-M01 | GFMS-Mod-feature-001 | • Stakeholder Register • Project schedule • Project Management Plan • Monthly/Weekly Project Status Report • Risks, Assumptions, Issues, Dependencies (RAID) Log • Deliverable Expectations Document (DED) |  | After 30 days of kick-off | 2024-10-15
GFMS-Milestone-M02 | GFMS-Mod-feature-002 | • Requirements Document Or its Agile equivalent like Product backlog • Technical System Specification Document • Testing risk assessment & Test Strategy • Traceability matrix |  | 2 months after project kick-off | 2024-12-16
GFMS-Milestone-M03 | GFMS-Mod-feature-003 | • Data mapping between CAFÉ and To-be system. • Data dictionary of To-be system. • Entity Relation diagram of the To-be database. • Proof of concept (POC) of data migration, completion report. • Full Data migration plan • Full Data migration completion report • Two Periodic extract, transform & load (ETL) completion report. • Release notes |  | After 2 months of previous milestone | 2025-02-14
GFMS-Milestone-M04 | GFMS-Mod-feature-004 | • Application specification doc or its Agile equivalent • Component specification doc or its Agile equivalent • Wireframes for New User interfaces & Reports • CI/CD pipeline & Devops tool set up & usage report. • Readiness report of integrated test environment with connectivity with interfacing application. • Unit testing results and SIT test results. • UAT completion report • Test completion report for fix of all major defects identified during UAT. • Release notes • Evidence of successful deployment • Post deployment system performance report |  | After 1 month of previous milestone | 2025-03-14
GFMS-Milestone-M05 | GFMS-Mod-feature-005 | • Application specification doc or its Agile equivalent • Component specification doc or its Agile equivalent • Wireframes for New User interfaces & Reports • CI/CD pipeline & Devops tool set up & usage report. • Readiness report of integrated test environment with connectivity with interfacing application. • Unit testing results and SIT test results. • UAT completion report • Test completion report for fix of all major defects identified during UAT. • Release notes • Evidence of successful deployment • Post deployment system performance report |  | After 1 month of previous milestone | 2025-04-15
GFMS-Milestone-M06 | GFMS-Mod-feature-006 | • Application specification doc or its Agile equivalent • Component specification doc or its Agile equivalent • Wireframes for New User interfaces & Reports • CI/CD pipeline & Devops tool set up & usage report. • Readiness report of integrated test environment with connectivity with interfacing application. • Unit testing results and SIT test results. • UAT completion report • Test completion report for fix of all major defects identified during UAT. • Release notes • Evidence of successful deployment • Post deployment system performance report |  | After 1 month of previous milestone | 2025-05-15
GFMS-Mod-feature-007
GFMS-Milestone-M07 | GFMS-Mod-feature-008 | • Application specification doc or its Agile equivalent • Component specification doc or its Agile equivalent • Wireframes for New User interfaces & Reports • CI/CD pipeline & Devops tool set up & usage report. • Readiness report of integrated test environment with connectivity with interfacing application. • Unit testing results and SIT test results. • UAT completion report • Test completion report for fix of all major defects identified during UAT. • Release notes • Evidence of successful deployment • Post deployment system performance report |  | After 1 month of previous milestone | 2025-06-16
GFMS-Mod-feature-009
GFMS-Milestone-M08 | GFMS-Mod-feature-010 | • Application specification doc or its Agile equivalent • Component specification doc or its Agile equivalent • Wireframes for New User interfaces & Reports • CI/CD pipeline & Devops tool set up & usage report. • Readiness report of integrated test environment with connectivity with interfacing application. • Unit testing results and SIT test results. • UAT completion report • Test completion report for fix of all major defects identified during UAT. • Release notes • Evidence of successful deployment • Post deployment system performance report |  | After 1 month of previous milestone | 2025-07-15
GFMS-Mod-feature-011
GFMS-Milestone-M09 | GFMS-Mod-feature-012 | • Application specification doc or its Agile equivalent • Component specification doc or its Agile equivalent • Wireframes for New User interfaces & Reports • CI/CD pipeline & Devops tool set up & usage report. • Readiness report of integrated test environment with connectivity with interfacing application. • Unit testing results and SIT test results. • UAT completion report • Test completion report for fix of all major defects identified during UAT. • Release notes • Evidence of successful deployment • Post deployment system performance report |  | After 1 month of previous milestone | 2025-08-15
GFMS-Milestone-M10 | GFMS-Mod-feature-013 | • A scaled down 'Low code development environment' set up in-line with Production environment. • Continuous Integration and DevOps tool set up for integration of Low code development environment with Quality Assurance or test environment. • An automated testing environment in which any newly developed module/process developed by GF team, can be tested & deployed by GF team. |  | After 2 months of milestone ‘GFMS-Milestone-M08’ which is last of the priority features deployment. | 2025-09-15
GFMS-Milestone-M11 | GFMS-Mod-feature-014 | · User training plan with coverage of each user community in scope. · User training & support documentation · Periodic status report of user training conducted and attendance summary. |  | After 3 months of milestone ‘GFMS-Milestone-M08’ which is last of the priority features deployment. | 2025-10-15
GFMS-Milestone-M12 | GFMS-Mod-feature-015 | Pre-deployment artifacts - • Back-out plan & testing of the same • Nonfunctional testing and security testing results and sign off from NYSED. - Penetration testing results - Vulnerability scanning test results. - Disaster Recovery (DR) Test results - Volume test Results - Availability / Stress testing results • Deployment Sequence of Events (SOE) • Deployment support ROTA • Communication plan during deployment. • Escalation matrix and dial in number for production defect triage. • Lessons learnt log. Post-deployment artifacts - • Post deployment system performance report • Post deployment warranty support ROTA and support helpdesk details. |  | After 1 month of user training completion milestone ‘GFMS-Milestone-M11’ | 2025-11-14
GFMS-Milestone-M13 | GFMS-Mod-feature-016 | • Application specification doc or its Agile equivalent • Component specification doc or its Agile equivalent • Wireframes for New User interfaces & Reports • CI/CD pipeline & Devops tool set up & usage report. • Readiness report of integrated test environment with connectivity with interfacing application. • Unit testing results and SIT test results. • UAT completion report • Test completion report for fix of all major defects identified during UAT. • Release notes • Evidence of successful deployment • Post deployment system performance report |  | After 2 months of final deployment milestone ‘GFMS-Milestone-M12’ | 2026-01-15
GFMS-Milestone-M14 | GFMS-Mod-feature-017 | · Project closure report. · Project management plan amended with closure details. |  | 3 months after final deployment milestone ‘GFMS-Milestone-M12’ | 2026-02-13
GFMS-Milestone-M15 | GFMS-Mod-feature-018 | · System performance report at the end of warranty · Licensed support documentation detailing SLA for issues based on severity. · Support management plan for 3-year support period detailing KPIs SLAs etc.. |  | 3 months after final deployment milestone ‘GFMS-Milestone-M12’. | 2026-02-13
GFMS-Milestone-M16 | GFMS-Mod-feature-019 | • Weekly system performance report including outages, SLA breaches. • Monthly product issues Root Cause Analysis (RCA) and permanent fix report. • Status report of enhancement activities. |  | After the completion of the warranty period and continuing for 3 years. | 2/16/26 - 2/13/29
|  | Total Cost: | 0
Hourly rate based on change complexity (to be used for change request estimation)
Change Complexity | Hourly rate (in whole Dollars) | Additional information from Vendor on how the complexity is defined. For example, in Story points or Function points or KLOC or Number of hours
Low
Medium
Complex

## Detailed view
RFP #24-023 GRANTS FINANCIAL MANAGEMENT SYSTEM (GFMS) COST PROPOSAL
CONTRACT TERM: SEPTEMBER 15, 2024 - FEBRUARY 13, 2029
Project Start Date |  | 2024-09-15
Development & Deployement End date |  | 2026-02-15
Support End Date |  | 2029-02-13
Note: 1) All deployment in plan below are to production Cloud environment which will not be fully rolled out to all users until all user training is complete. CAFÉ mainframe will be live until all features are live in to-be Cloud application. 2) All deliverables should be reviewed & approved by NYSED. Deliverables should be in 'NYSED approved' status, only then the milestone is considered as met.
Milestone Reference | Feature Reference | Feature Name | Feature Description | Milestone | Milestone Timeline | Tentative Milestone Dates | Success Criteria | Deliverable Reference | Deliverables | Additional Information from NYSED
GFMS-Milestone-M01 | GFMS-Mod-feature-001 | Project management activities | • Initial project kick-off • Establish governance model • Create project plan • Establish scope • Create Initial RAID log. | Project kick-off completed and project management plan signed off | After 30 days of kick-off | 2024-10-15 | • Project Kick-off meeting completed. • Initial version of Project management plan signed off by NYSED. • RAID log created and process established for continuous updates | D100 Project Management Activities | • Stakeholder Register • Project schedule • Project Management Plan • Monthly/Weekly Project Status Report • Risks, Assumptions, Issues, Dependencies (RAID) Log • Deliverable Expectations Document (DED)
GFMS-Milestone-M02 | GFMS-Mod-feature-002 | As is system understanding and to-be system design | • As-is system understanding completed by vendor. • High level requirements for the to-be systems documented. • To-be system technical architecture finalized. | As-is system understanding complete and product backlog with requirements created. User stories for at least the first 3 sprints are documented. | 2 months after project kick-off | 2024-12-15 | • Vendor completed As-is system understanding. • Product backlog with Epics, Features, and user stories for first 3 sprints created. • Technical design of To-be system signed off by NYSED | D200 – As-is system understanding & To-be system design | • Requirements Document Or its Agile equivalent like Product backlog • Technical System Specification Document • Testing risk assessment & Test Strategy • Traceability matrix
GFMS-Milestone-M03 | GFMS-Mod-feature-003 | Data migration from CAFÉ to To-be application | • Data mapping between As-is CAFÉ and To-be system. • Data migration from Mainframe CAFÉ database to To-be system database. • Verify the completeness and correctness of the data transferred. • Establish an 'Extract-Transform-Load' (ETL) process for periodic incremental data migration from CAFE mainframe to To-be system. | Data migration complete and process for periodic data migration from As-is to To-be successfully run at least 2 iterations. | After 2 months of previous milestone | 2025-02-15 | • Data mapping of As-is and To-be systems complete. • Data dictionary of to-be system created. • Dev, test & production environment set up complete. • POC completed over a subset of data migration. Completeness and correctness of the same approved by NYSED • After successful POC, full data migration from As-is to To-be system successful. Completeness and correctness of the same approved by NYSED • At least 2 successful runs of the periodic incremental data migration from As-is to To-be system | D300 Data Migration | • Data mapping between CAFÉ and To-be system. • Data dictionary of To-be system. • Entity Relation diagram of the To-be database. • Proof of concept (POC) of data migration, completion report. • Full Data migration plan • Full Data migration completion report • Two Periodic extract, transform & load (ETL) completion report. • Release notes | During POC, the data migration ETL process will be set up. Once successful, the POC & full data migration will be ad hoc runs. Post which the ETL will be set up to run for a pre-defined periodicity
GFMS-Milestone-M04 | GFMS-Mod-feature-004 | Federal/State award entry, Grant program entry, Any other ref data entry | • Vendor should provide a home page and the layout of the features from the home page like a portal layout. • Appropriate screens are to be provided for entry of hierarchy data like Federal/State award & Grant program which will be parent to the individual LEA grants and their vouchers and expenditure details. | After addressing all major defects identified during UAT, feature deployment signed off by NYSED. Basis which, Federal/State award entry, Grant program entry, any other ref data entry features deployment completed in to-be system. | After 1 month of previous milestone | 2025-03-15 | • Federal & State award entry, Grant program entry, any other ref data entry features developed. • All testing including UAT by NYSED complete. • All major defects addressed. • Features deployed in To-be production environment, which is not fully rolled out to all users. | • D400 User Interface • D500 UX Design and Information Architecture Deliverables • D600 Integration • D700 Quality Assurance Testing • D800 Deployment | • Application specification doc or its Agile equivalent • Component specification doc or its Agile equivalent • Wireframes for New User interfaces & Reports • CI/CD pipeline & Devops tool set up & usage report. • Readiness report of integrated test environment with connectivity with interfacing application. • Unit testing results and SIT test results. • UAT completion report • Test completion report for fix of all major defects identified during UAT. • Release notes • Evidence of successful deployment • Post deployment system performance report
GFMS-Milestone-M05 | GFMS-Mod-feature-005 | FS-10 Grant budget workflow | • FS10 creation/submission by LEA, PO review/approval, followed by Grant Finance team’s budget review. • Bulking and transmission to OF, from OF to SFS, grant funds sent out to LEA by SFS. • Expenditure tracking & budget controls associated with FS-10 | After addressing all major defects identified during UAT, feature deployment signed off by NYSED. Basis which, FS-10 Grant budget workflow features deployment completed in production to-be system. | After 1 month of previous milestone | 2025-04-15 | • FS-10 Grant budget workflow features and associated expenditure tracking & budget control features deployed. • Interfacing with SEDREF, OF, SFS established, and transmissions sent to and from interfacing systems. • Expenditure tracking and budget control feature for FS-10 works as expected and functionality approved by NYSED. • All testing including UAT by NYSED complete. • All major defects addressed. • Features deployed in To-be production environment, which is not fully rolled out to all users. | • D400 User Interface • D500 UX Design and Information Architecture Deliverables • D600 Integration • D700 Quality Assurance Testing • D800 Deployment | • Application specification doc or its Agile equivalent • Component specification doc or its Agile equivalent • Wireframes for New User interfaces & Reports • CI/CD pipeline & Devops tool set up & usage report. • Readiness report of integrated test environment with connectivity with interfacing application. • Unit testing results and SIT test results. • UAT completion report • Test completion report for fix of all major defects identified during UAT. • Release notes • Evidence of successful deployment • Post deployment system performance report
GFMS-Milestone-M06 | GFMS-Mod-feature-006 | FS-10A Grant budget workflow | • FS10A creation/submission by LEA, PO review/approval, followed by budget amendment by GF. • Expenditure tracking & budget controls associated with FS-10A | After addressing all major defects identified during UAT, feature deployment signed off by NYSED. Basis which, FS-10A Grant budget amendment and FS-25 Voucher creation workflow features deployment completed in production to-be system. | After 1 month of previous milestone | 2025-05-15 | • FS-10A Grant budget workflow features and associated expenditure tracking & budget control features deployed. • FS-25 Voucher creation workflow features and associated expenditure tracking & budget control features deployed. • Interfacing with SEDREF, OF, SFS established, and transmissions sent to and from interfacing systems. • All testing including UAT by NYSED complete. • All major defects addressed. • Features deployed in To-be production environment, which is not fully rolled out to all users. | • D400 User Interface • D500 UX Design and Information Architecture Deliverables • D600 Integration • D700 Quality Assurance Testing • D800 Deployment | • Application specification doc or its Agile equivalent • Component specification doc or its Agile equivalent • Wireframes for New User interfaces & Reports • CI/CD pipeline & Devops tool set up & usage report. • Readiness report of integrated test environment with connectivity with interfacing application. • Unit testing results and SIT test results. • UAT completion report • Test completion report for fix of all major defects identified during UAT. • Release notes • Evidence of successful deployment • Post deployment system performance report
| GFMS-Mod-feature-007 | FS-25 Voucher create & SFS transmission workflow | • FS-25 creation/submission by LEA, followed by GF review/approval. • Bulking and transmission to OF, from OF to SFS and then Grant funds sent out to LEA by SFS. • Expenditure tracking & budget controls associated with FS-25
GFMS-Milestone-M07 | GFMS-Mod-feature-008 | FS-10F work flow | • FS-10F workflow and expenditure tracking & budget controls associated with FS-10F. • Bulking and transmission to OF, from OF to SFS. • Expenditure tracking & budget controls associated with FS-10F. | After addressing all major defects identified during UAT, feature deployment signed off by NYSED. Basis which, FS-10F and final set of expenditure tracking & budget controls workflow features deployment completed in production to-be system. | After 1 month of previous milestone | 2025-06-15 | • FS-10F workflow feature and associated expenditure tracking & budget control features deployed. • Interfacing with SEDREF, OF, SFS established, and transmissions sent to and from interfacing systems. • Any additional expenditure tracking & budget controls features deployed. • All testing including UAT by NYSED complete. • All major defects addressed. • Features deployed in To-be production environment, which is not fully rolled out to all users. | • D400 User Interface • D500 UX Design and Information Architecture Deliverables • D600 Integration • D700 Quality Assurance Testing • D800 Deployment | • Application specification doc or its Agile equivalent • Component specification doc or its Agile equivalent • Wireframes for New User interfaces & Reports • CI/CD pipeline & Devops tool set up & usage report. • Readiness report of integrated test environment with connectivity with interfacing application. • Unit testing results and SIT test results. • UAT completion report • Test completion report for fix of all major defects identified during UAT. • Release notes • Evidence of successful deployment • Post deployment system performance report
| GFMS-Mod-feature-009 | Expenditure tracking feature | • Rest of the Expenditure tracking & budget controls features
GFMS-Milestone-M08 | GFMS-Mod-feature-010 | Reporting feature | • Define layout of report & create them from To-be application. • Generate scheduled reports which are replacements of existing reports. • Ability to dynamically generate on-demand reports and schedule the same for periodic runs. • Ability to generate OnDemand one-off reports using a report generation interface | After addressing all major defects identified during UAT, feature deployment signed off by NYSED. Basis which, reporting feature and reconciliation feature deployment completed in production to-be system. | After 1 month of previous milestone | 2025-07-15 | • Reporting feature deployed. • Reconciliation feature developed. • All testing including UAT by NYSED complete. • All major defects addressed. • Features deployed in To-be production environment, which is not fully rolled out to all users. | • D400 User Interface • D500 UX Design and Information Architecture Deliverables • D600 Integration • D700 Quality Assurance Testing • D800 Deployment | • Application specification doc or its Agile equivalent • Component specification doc or its Agile equivalent • Wireframes for New User interfaces & Reports • CI/CD pipeline & Devops tool set up & usage report. • Readiness report of integrated test environment with connectivity with interfacing application. • Unit testing results and SIT test results. • UAT completion report • Test completion report for fix of all major defects identified during UAT. • Release notes • Evidence of successful deployment • Post deployment system performance report
| GFMS-Mod-feature-011 | Reconciliation feature | • Delivery of automated reconciliation functionality involving interfacing applications like SFS, the interface could be an API.
GFMS-Milestone-M09 | GFMS-Mod-feature-012 | Any additional User notifications/ reporting features | • For each workflow of the to-be system, notifications should be sent to appropriate user/user groups. While this feature is part of each functionality deployment above, this milestone is for the build/set up and deployment of any additional notification/reporting features requested. | After addressing all major defects identified during UAT, feature deployment signed off by NYSED. Basis which, any additional User notifications/ reporting feature deployment completed in production to-be system. | After 1 month of previous milestone | 2025-08-15 | • Any additional functionality & new reports or modifications deployed. • All testing including UAT by NYSED complete. • All major defects addressed. • Features deployed in To-be production environment, which is not fully rolled out to all users. | • D400 User Interface • D500 UX Design and Information Architecture Deliverables • D600 Integration • D700 Quality Assurance Testing • D800 Deployment | • Application specification doc or its Agile equivalent • Component specification doc or its Agile equivalent • Wireframes for New User interfaces & Reports • CI/CD pipeline & Devops tool set up & usage report. • Readiness report of integrated test environment with connectivity with interfacing application. • Unit testing results and SIT test results. • UAT completion report • Test completion report for fix of all major defects identified during UAT. • Release notes • Evidence of successful deployment • Post deployment system performance report
GFMS-Milestone-M10 | GFMS-Mod-feature-013 | Handover & support of Development & Test environment | • Since the to-be application will be low code, for future enhancements, there should be a user interface driven method to build code which the GF business or BAs or a tech resource can use. • The vendor should set up and maintain a set of Development & Test environments that will be periodically synchronized with prod version in terms of code & data. | Vendor provides environments to NYSED GF business team to develop new functionality using low code UI driven features, ability to test and deploy them into production environment. | After 2 months of milestone ‘GFMS-Milestone-M08’ which is last of the priority features deployment. | 2025-09-15 | • A set of Low-code user interface (UI) driven development environment and test environment with tools for deployment set up and handed over to NYSED GF business team. | D1100 Environment | • A scaled down 'Low code development environment' set up in-line with Production environment. • Continuous Integration and DevOps tool set up for integration of Low code development environment with Quality Assurance or test environment. • An automated testing environment in which any newly developed module/process developed by GF team, can be tested & deployed by GF team.
GFMS-Milestone-M11 | GFMS-Mod-feature-014 | Completion of user training | • Plan for To-be system user training sessions for all users in tranches | user training completed for 99% of the intended users of the to-be system. | After 3 months of milestone ‘GFMS-Milestone-M08’ which is last of the priority features deployment. | 2025-10-15 | • User training complete for 99% of the intended users of the to-be system. | D900 Training | · User training plan with coverage of each user community in scope. · User training & support documentation · Periodic status report of user training conducted and attendance summary.
GFMS-Milestone-M12 | GFMS-Mod-feature-015 | Final deployment | • During this period, the to-be solution will be rolled out to all users. CAFÉ mainframe system will be stopped from usage in a phased manner. | Successful roll out of all GFMS features in the to-be system, to all intended users. | After 1 month of user training completion milestone ‘GFMS-Milestone-M11’ | 2025-11-15 | • Successful roll out of to-be system to all intended users. • All GFMS functionality available in the to-be systems and the As-is system is ready for decommission. | D800 Deployment | Pre-deployment artifacts - • Back-out plan & testing of the same • Nonfunctional testing and security testing results and sign off from NYSED. - Penetration testing results - Vulnerability scanning test results. - Disaster Recovery (DR) Test results - Volume test Results - Availability / Stress testing results • Deployment Sequence of Events (SOE) • Deployment support ROTA • Communication plan during deployment. • Escalation matrix and dial in number for production defect triage. • Lessons learnt log. Post-deployment artifacts - • Post deployment system performance report • Post deployment warranty support ROTA and support helpdesk details.
GFMS-Milestone-M13 | GFMS-Mod-feature-016 | Any medium/low priority defect fix & any agreed enhancements | • Any medium/low priority defects identified in any earlier phases, that were categorized as good-to-have, must be addressed here. | All medium & low priority defects fixed and deployed. | After 2 months of final deployment milestone ‘GFMS-Milestone-M12’ | 2026-01-15 | • All medium/low priority defects fixed and deployed | • D400 User Interface • D500 UX Design and Information Architecture Deliverables • D600 Integration • D700 Quality Assurance Testing • D800 Deployment | • Application specification doc or its Agile equivalent • Component specification doc or its Agile equivalent • Wireframes for New User interfaces & Reports • CI/CD pipeline & Devops tool set up & usage report. • Readiness report of integrated test environment with connectivity with interfacing application. • Unit testing results and SIT test results. • UAT completion report • Test completion report for fix of all major defects identified during UAT. • Release notes • Evidence of successful deployment • Post deployment system performance report
GFMS-Milestone-M14 | GFMS-Mod-feature-017 | Project closure activities | • Handover of User support documentation, project closure documents, stopping of periodic ETL from As-is system, revoking of to-be system access to vendors who are not involved in continued support etc. | Project closure document approved by NYSED, and ongoing support mechanism established and approved by NYSED. | 3 months after final deployment milestone ‘GFMS-Milestone-M12’ | 2026-02-15 | • All user support documents handed over to NYSED. • Project Closure report approved by NYSED. • Mechanism for on-going support established. | D100 Project Management Activities | · Project closure report. · Project management plan amended with closure details.
GFMS-Milestone-M15 | GFMS-Mod-feature-018 | Completion of warranty. | End of 60 days (about 2 months) warranty period of to-be system post final deployment. | All warranty period defects fixed, and system performance parameters approved by NYSED. Support management plan for 3-year support period detailing KPIs & SLAs. | 3 months after final deployment milestone ‘GFMS-Milestone-M12’. | 2026-02-15 | • All warranty period defects fixed and the same approved by NYSED. • Fully live to-be system performance, Availability and all other Non-functional requirements met and approved by NYSED. • For the next milestone, vendor creates documentation of acceptable system performance & SLAs for production defects applicable during the 3 years support period. This support plan is approved by NYSED. • In the support plan, there should be a mutually agreed penalty clause for breaching the accepted SLAs & system performance issues. • In the support plan, there should be a definition of a maximum size & complexity of enhancement that will be part of the 3 years support cost. | D1000 Warranty Support | · System performance report at the end of warranty · Licensed support documentation detailing SLA for issues based on severity. · Support management plan for 3-year support period detailing KPIs SLAs etc..
GFMS-Milestone-M16 | GFMS-Mod-feature-019 | Start of 3 years support of the To-be application | As part of the current RPF cost proposal, Vendor should provide an estimate for 3 years of support for the to-be application. During this period Vendor will be responsible for; 1) Maintenance of the To-be system within a mutually agreed performance level. 2) Support all defects/outages of the production live application within pre-defined Service level agreements (SLAs). 3) During this period vendor should take up any change request from NYSED, of a pre-defined without any additional cost. 4) Vendor should apply any hardware or software service-packs/upgrades to maintain the to-be system with pre-defined performance levels. 5) Vendor should maintain the development & Test environments handed over to NYSED, such that it is fully synced up with Production in terms of data and code. | Vendor should conduct review meetings & share periodic reports detailing the performance of to-be system against pre-defined parameters, approved by NYSED in milestone ‘GFMS-Milestone-M15 – completion of warranty’. | After the completion of the warranty period and continuing for 3 years. | February 16th, 2026 until February 13th, 2029 | • To-be system maintained within agreed performance limits and able to meet NYSED Grants Finance business requirements. • Support of to-be system as per the KPIs & SLAs established in the Support plan. • Monthly review meeting conducted and activities processing per plan. | D1200 3 year Support | • Weekly system performance report including outages, SLA breaches. • Monthly product issues Root Cause Analysis (RCA) and permanent fix report. • Status report of enhancement activities.
Formulas:
Tentative Milestone Dates = [Tentative Milestone Dates, row above]+61

## Subcontracting
Subcontracting Form
Name of Subcontractor | M/WBE* | Entity Type | Work Description | Year 1 Cost | Multi-Year Cost (including Year 1)
| ¨ MBE | ¨ For Profit
| ¨ WBE | ¨ Not –For-Profit
| ¨ MBE | ¨ For Profit
| ¨ WBE | ¨ Not –For-Profit
| ¨ MBE | ¨ For Profit
| ¨ WBE | ¨ Not –For-Profit
| ¨ MBE | ¨ For Profit
| ¨ WBE | ¨ Not –For-Profit
| ¨ MBE | ¨ For Profit
| ¨ WBE | ¨ Not –For-Profit
| ¨ MBE | ¨ For Profit
| ¨ WBE | ¨ Not –For-Profit
| ¨ MBE | ¨ For Profit
| ¨ WBE | ¨ Not –For-Profit
|  |  |  | Total Multi-Year Subcontracting Costs | 0
|  |  |  | Total Multi-Year Project Budget | 0
|  |  |  | Total Multi-Year Subcontracting Costs divided by Total Multi-Year Budget (%)** | #DIV/0!
*Indicate whether the subcontractor is a Minority or Women–Owned Business Enterprise. Leave box blank if subcontractor is neither.
**Subcontracting is limited to thirty percent (30%) of the total contract budget.

## MWBE
MWBE Purchases Form
Table 1: Minority Business Enterprise (MBE)
Name of Vendor | Type of Services or Supplies | Year 1 Cost | Multi-Year Cost (including Year 1)
|  | Total MBE Costs | 0
|  | Total Budget | 0
|  | Total MBE Costs divided by Total Budget (%) | #DIV/0!
Table 2: Women-Owned Business Enterprise (WBE)
Name of Vendor | Type of Services or Supplies | Year 1 Cost | Multi-Year Cost (including Year 1)
|  | Total WBE Costs | 0
|  | Total Budget | 0
|  | Total WBE Costs divided by Total Budget (%) | #DIV/0!